STARTUP OPERATIONS

PLAYBOOK

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Project Tracking  ·  Team Delegation  ·  Client Delivery  ·  Compliance

Esther Istifanus

Operations Analyst  ·  ABU, Zaria  ·  2025

# Introduction

This playbook documents the operational systems, frameworks, and processes built and refined while leading operations at the ABU Investment Society Management Consulting Division and serving as Operations Officer at P2P (Plastic to Paint).

It is designed to be modular — pick the section most relevant to your stage and drop it directly into your workflow. Every framework here has been tested in a live operating environment with real clients and real deadlines.

Who this is for Early-stage startups setting up ops from scratch Operations leads inheriting a disorganised team Founders who need to hand off ops to a first hire Consulting teams managing multiple client engagements

| Section | What it covers |
| --- | --- |
| 01 Project Tracking | Intake, scoping, milestones, and tracker setup |
| 02 Team Delegation | Role clarity, task allocation, and performance reviews |
| 03 Client Delivery | Communication cadence, sign-off process, handover |
| 04 Compliance | Data handling, meeting governance, audit trail |
| 05 AI Automation | Where to apply AI tools to each ops workflow |

# 01  Project Tracking

The single biggest ops failure in early-stage teams is invisible work — tasks that exist in someone's head, not in a shared system. This section establishes a lightweight but complete project tracking infrastructure.

## 1.1  Project Intake Process

Every new project must go through intake before any work begins. Skipping this step is the root cause of scope creep, missed deadlines, and client dissatisfaction.

Intake checklist (complete before kickoff):

- Client name, primary contact, and communication channel

- Project brief: one paragraph defining the deliverable

- Scope boundary: explicitly state what is NOT included

- Timeline: start date, key milestones, final deadline

- Success criteria: how will client sign off that it is done?

- Team assignment: lead analyst and supporting member

- Data requirements: what info is needed, from whom, by when

If you cannot complete this checklist, the project is not ready to start. Push back on the client or requestor until it is.

## 1.2  Project Tracker Structure

Build one master tracker in Google Sheets. One tab per active project, one summary tab for leadership view. Below is the column structure for each project tab.

| # | Task | Owner | Status |
| --- | --- | --- | --- |
| 01 | Project intake form completed | Ops Lead | Template |
| 02 | Kickoff meeting scheduled | Ops Lead | Template |
| 03 | Team assigned and briefed | Ops Lead | Template |
| 04 | Week 1 deliverable submitted | Lead Analyst | Template |
| 05 | Mid-project check-in done | Ops Lead | Template |
| 06 | Draft deliverable reviewed | Ops Lead | Template |
| 07 | Client feedback incorporated | Lead Analyst | Template |
| 08 | Final deliverable submitted | Lead Analyst | Template |
| 09 | Client sign-off received | Ops Lead | Template |
| 10 | Project retrospective completed | All | Template |

Replace 'Template' with 'To Do', 'In Progress', 'Done', or 'Blocked'. Review the tracker in every weekly ops meeting.

## 1.3  Milestone Cadence

Standardise your delivery rhythm so every project follows the same pattern regardless of complexity.

| Week | Milestone |
| --- | --- |
| Week 1 | Kickoff complete. Research and data collection underway. |
| Week 2 | First draft of core deliverable submitted internally. |
| Week 3 | Ops Lead review and revisions. Client preview if needed. |
| Week 4 | Final deliverable submitted. Client feedback window opens. |
| Week 5 | Sign-off and handover. Retrospective within 48 hours. |

For projects shorter than 4 weeks, compress the cadence proportionally. Never skip the retrospective — it feeds the next project.

# 02  Team Delegation

Delegation fails when ownership is unclear. This section gives you three tools: a role clarity matrix, a task allocation framework, and a lightweight performance review system.

## 2.1  Role Clarity Matrix

For every major activity, define who is Responsible, Accountable, Consulted, and Informed (RACI). A team of 3–5 people only needs this for the 8–10 recurring activities that happen every project.

| Activity | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Project intake | Ops Lead | Ops Lead | — | Team |
| Task allocation | Ops Lead | Ops Lead | Analysts | Client |
| Research / analysis | Lead Analyst | Ops Lead | Ops Lead | — |
| Draft deliverable | Lead Analyst | Ops Lead | — | — |
| Quality review | Ops Lead | Ops Lead | Lead Analyst | — |
| Client communication | Ops Lead | Ops Lead | Analysts | — |
| Data compliance | Ops Lead | Ops Lead | All | — |
| Retrospective | All | Ops Lead | — | Leadership |

## 2.2  Task Allocation Principles

- Stretch vs. confirm. Match complexity to capability:

Give analysts tasks slightly above their current level to build capability, not tasks so far beyond it that they stall.

- ASAP is not a deadline. Set explicit deadlines, not 'ASAP':

Every task gets a day and time. 'By Thursday 5pm' is a deadline. 'When you can' is not.

- Shared ownership = no ownership. One owner per task:

If two people are responsible, one of them is not. Name the lead.

- No silent stuck. Surface blockers in 24 hours:

If an analyst is blocked, they flag it within 24 hours. The Ops Lead's job is to unblock, not to wait.

## 2.3  Weekly Performance Check-in

Run a 15-minute weekly check-in for each analyst. Structure it identically every week — predictability reduces anxiety and increases honesty.

15-Minute Weekly Check-in Template 1. What did you complete this week? (3 min) 2. What are you working on next week? (3 min) 3. What is blocking you or slowing you down? (4 min) 4. One thing you want feedback on from me? (3 min) 5. Ops Lead closes with one specific positive observation. (2 min)

Always end with a positive observation. Not generic praise — specific and earned. It sets the tone for the next week.

# 03  Client Delivery

Delivery is not just handing over a file. It is a managed sequence from first contact to sign-off that builds trust, captures feedback, and sets up the next engagement.

## 3.1  Communication Cadence

| Touchpoint | Purpose & format |
| --- | --- |
| Kickoff call | Align on scope, timeline, and success criteria. 45 mins max. Ops Lead facilitates. |
| Week 2 update | Written summary: progress, next steps, any risks. Sent by email. 3 paragraphs. |
| Mid-project check-in | 15-min call if project is 4+ weeks. Optional for short projects. |
| Draft preview | Share draft 48 hours before final delivery. Invite one round of feedback only. |
| Final delivery | Polished document plus a one-page executive summary. Delivered by agreed channel. |
| Sign-off request | Explicit request for written confirmation. Do not assume silence = approval. |
| Retrospective invite | 48-hour post sign-off. 20-minute call or async survey. |

## 3.2  Deliverable Standards

Every deliverable must meet these standards before it leaves the team.

- One-page executive summary at the front — always.

- All figures and data sourced and cited.

- Spell-checked and reviewed by Ops Lead, not just the author.

- Formatted consistently: one font, consistent heading hierarchy, no mixed styles.

- File named correctly: ClientName_DeliverableName_YYYYMMDD

- Sent as PDF unless client explicitly requests editable format.

## 3.3  Sign-Off Protocol

Never close a project without written sign-off. A verbal 'looks good' is not sign-off.

Sign-Off Email Template Subject: [Project Name] — Final Deliverable & Sign-Off Request Hi [Client Name], Please find attached the final deliverable for [Project Name]. This incorporates all feedback received on [date]. Could you please confirm receipt and acceptance by replying to this email? A simple 'confirmed' works — we just need written record. It has been a pleasure working with you. We will follow up separately for a brief retrospective. Best, [Your Name]

# 04  Compliance & Governance

Startups and early-stage consulting teams often skip compliance because it feels like a large-company concern. It is not. Mishandled client data, undocumented decisions, and poor meeting governance all compound into reputational and operational risk.

## 4.1  Data Handling Rules

- designated shared folder only. Client data lives in one place:

No client files on personal devices, personal Google Drives, or personal email.

- need-to-know only. Access is role-based:

Only the lead analyst and Ops Lead have access to raw client data.

- within 30 days of sign-off. Data is deleted post-project:

Retain only the final deliverable and sign-off confirmation.

- Never share client data with a third party without written consent.

- If data is accidentally exposed, notify the client within 24 hours.

## 4.2  Meeting Governance

| Rule | Why it matters |
| --- | --- |
| Every meeting has an agenda sent 24h before | No agenda = no preparation = wasted time |
| One person takes notes in real time | Memory is unreliable; notes are not |
| Action items named with owner + deadline | Decisions without owners do not get executed |
| Notes distributed within 2 hours of meeting end | People forget; write it down fast |
| No meeting longer than 60 minutes without a break | Attention collapses; quality collapses with it |
| If a meeting could be an email, send the email | Default to async; reserve meetings for decisions |

## 4.3  Audit Trail

Maintain a running log of key decisions, client approvals, and data access events. This protects the team and the client.

| # | Task | Owner | Status |
| --- | --- | --- | --- |
| D01 | Project intake form completed and filed | Ops Lead | Template |
| D02 | Client NDA/confidentiality agreement signed | Ops Lead | Template |
| D03 | Data access log updated on receipt | Ops Lead | Template |
| D04 | Mid-project written update sent and filed | Ops Lead | Template |
| D05 | Draft preview sent with timestamp | Ops Lead | Template |
| D06 | Client feedback received and documented | Lead Analyst | Template |
| D07 | Written sign-off received and filed | Ops Lead | Template |
| D08 | Data deleted within 30 days of sign-off | Ops Lead | Template |

# 05  AI Automation Layer

Every framework in this playbook has a corresponding point where AI automation reduces time, increases consistency, or surfaces insights that manual review would miss.

These are not hypothetical — each automation below maps directly to a workflow built and demonstrated in this portfolio.

## 5.1  Automation Map

| Ops workflow | AI automation | Tool | Time saved |
| --- | --- | --- | --- |
| Investor / stakeholder updates | Auto-draft polished update email from raw ops notes | Claude API | ~2 hrs/month |
| Meeting notes | Extract action items and owners from raw transcript | Claude API | ~1 hr/meeting |
| Project status reports | Summarise tracker data into executive briefing | Claude + Sheets | ~1.5 hrs/week |
| Onboarding new analysts | Generate role-specific checklist from playbook | Claude API | ~3 hrs/hire |
| KPI dashboards | Auto-update charts from structured data input | Python + Pandas | ~4 hrs/month |
| Compliance audit trail | Flag missing documentation automatically | Sheets + Scripts | ~2 hrs/month |

## 5.2  Implementation Principles

- Automation handles structure; humans handle judgment. Automate the repeatable, not the relational.

- AI drafts. Humans approve. Always keep a human review step before client-facing output.

- A well-engineered prompt is a repeatable asset. Document the prompt, not just the output.

- The biggest time sink is the best automation target. Start with the workflow that costs you the most time.

The rule of thumb for ops automation If you do it more than twice a month and it follows a consistent structure, it can be automated. If it requires a judgment call every time, keep it human. If it touches a client directly, always add a human review step.

# A Note on This Playbook

This document was built from real operational experience — running live consulting engagements at ABU, scaling P2P from a funded idea to ₦9M in revenue, and supporting deal origination at Kuramo Capital.

Every framework here has been tested against real deadlines, real clients, and real consequences. Nothing is hypothetical.

The AI automation layer represents where I believe operations is heading for early-stage startups in Africa and globally — not AI replacing operators, but operators who know how to build with AI outperforming those who don't.

Contact Esther Istifanus · Operations Analyst Email: Jesther402@gmail.com Location: Zaria, Nigeria Available for: Operations roles at startups, VC-backed companies, and consulting firms